## Sheet1
BUGS
Defect # | Priority | Status | Version Found | Version Fixed | Screen | Settings | Issue | Fix Description
1 | 1 | FIX | 1.3.1 | 1.3.3 | STRIPS | Strip mode = CONT; Settings->Delay > 0 | After 1st count, the count is << 0.1s per tick. | Procedure "StartMainTimer" did not set TIMER_COUNT if called by clkCountIn.Timer block with count-in > 0 (i.e. we want a delay between strips).
2 | 1 | NS | 1.3.2 |  | STRIPS | Any | Hitting STOP in mid sequence leaves the timer in an undefined state. | Need to reset the timer to where it was when START was hit.
3 | 3 | NS | 1.3.2 |  | STRIPS | Any | Can move to another tab when strips timing is in progress | Need to reset the timer if move away from STRIPS tab mid-strip.
4 | 2 | IP | 1.3.2 |  | STRIPS | Strip mode = CONT; SETTINGS tab - Delay = 0 | 1st beep too low freq and too long - possibly too quiet | Should be higher freq (but lower than end-beep) and shorter.
5 | 1 | FIX | 1.3.2 | 1.3.3 | STRIPS | Any | Strip base time value at the botom of the screen [lblStripBaseTime] is loaded on app startup but the display is not set to this value. | Do not load this value on startup. Forced user to set the strip base-time via the display and the SET button.