## Sheet1
DEFECTS AND ENHANCEMENTS
Issue Number | Priority | Status | Version Found | Version Fixed | Screen | Settings | Issue | Fix Requirements | Release Note
1 | 1 | FIX | 1.3.2 | 1.3.3 | STRIPS | Strip mode = CONT; Settings->Delay > 0 (i.e. Continuous mode with a delay between strips) | After 1st count, the count is << 0.1s per tick. | Timer should always count in 100ms incements. | Procedure "StartMainTimer" did not set START_MS if called by the clkCountIn.Timer block with count-in > 0 (i.e. when we want a delay between strips).
2 | 3 | FIX | 1.3.2 | 1.3.3 | STRIPS | Any | Hitting STOP in mid Strips sequence leaves the timer in an undefined state. | Hitting [RST] in STRIPS mode should reload the strip base time value to allow a new strip-mode timing with the previous base time value. | In STRIPS mode, [RST] now works to reset the timer to the value previously set by the [SET] button if the timer is paused. In MAIN timer mode, it works as before.
3 | 1 | FIX | 1.3.2 | 1.3.3 | STRIPS | Any | Strip base time value at the botom of the screen [lblStripBaseTime] is loaded on app startup but the display is not set to this value. | Do not load this value on startup. Force user to set the strip base-time via the display and the SET button. | Value no longer loaded on startup.
4 | 2 | FIX | 1.3.2 | 1.3.3 | STRIPS | Timer counting | When moving to Strips or Main timing mode tabs, the timer switches to the new mode. Timing is disrupted and confusing to the user. | Timer should not switch mode when changing tab. | New globals STRIPS_MODE _ENABLED and MAIN_MODE_ENABLED used to set the mode (previously relied on visibility of the Strips mode screen to detect which mode of timing to use).
5 | 2 | FIX | 1.3.2 | 1.33 | ALL | Any | Ticks and beeps inconsitent in volume and frequency and length | Improve the quality of the sounds. | Lowered end-beep and incresed strip-end warning beep frequencies. Tick shorter and colume increased to fit other sounds better. Trimmed all silence from samples.
6 | 1 | N/S | 1.3.3 |  | N/A | N/A | Manual requires updating to reflect the additional functionality and defect fixes. | To be updated
7
8
9
10